## group_information
Group Name | DietPal
Usernames | Activity 1 Role | Activity 2 Role | Activity 3 Role
bradley.lamptey | scribe | steward | secretary
ama.amoateng | steward | secretary | steward
edinam.agyeman | secretary | chairman | scribe
dominic.owusu | chairman | scribe | chairman

## learning_objectives
Objective ID | Date | Objective Title | Objective Description | Resources Identified | Other Comments | Group Status | Group Status Comments
1 | 2025-09-15 | Learning HTML Tags | Learn HTML Tags including html, head, body, script and style |  |  | 100% | We met and completedHTML
2 | 2025-09-15 | Learning CSS | Learning how to include CSS in HTML including inline, in a style tag or using the link | lecture slides, our notes, examples from tutorials.com |  | 100% | We finished CSS learning and each understands
3 | 2025-09-15 | Learning JavaScript Basics | Learn how to include JS to display to console, and to change the elements style | lecture slides, and examples from mozilla. |  | 0% | Completed
4 | 2025-09-15 | JavaScript intermediary | Using JavaScript to add content to the page (innerHTML, createElement and appendChild) | lecture slides and to check on some blogs found. |  | 20% | We started to discuss but will finish later
5 | 2025-09-16 | Learning Backend(PHP) | Learn to connect to servers and store data dynamically in database. |  |  | 80% | In progress

## project_requirements
Objective ID | Date | Objective Title | Objective Description | Resources Identified | Other Comments | Group Status | Group Status Comments
1 | 2025-10-15 | Create Faculty Dashboard HTML Page | Build a responsive Faculty Intern Dashboard using semantic HTML (header, main, section, aside, nav) to display courses, stats, and activities. | Lecture slides, previous code, W3Schools | Used existing dashboard structure to maintain layout consistency. | 100% | Discussions on HTML completed and filenames agreed
2 | 2025-10-15 | Apply Dashboard Styling | Implement CSS for dashboard (grid layout, color palette, responsiveness, hover effects). | previous CSS file | Applied color scheme. | 100% | Discussion on the registration page including what to have on the forms.
3 | 2025-10-16 | Implement JavaScript Interactivity | Add client-side interactivity (navigation, dynamic content injection). Initially used fetch() to connect to endpoints; later adapted to server-side approach where needed. | JS notes, The_Dashboard.js | Handles injecting attendance form/table into #contentArea and UI behavior. | 100% | Not yet met to discuss
4 | 2025-10-17 | Create Database Schema & Tables | Design and create courses and attendance tables in MySQL with appropriate columns and foreign key. | phpMyAdmin, SQL cheatsheets | Tables created: courses(course_id, course_name, instructor, interns) and attendance(id, student_name, course_id, date, status). | 100%
5 | 2025-10-17 | Connect PHP to Database | Implement database.php and test connectivity from local XAMPP and remote server. | XAMPP, phpMyAdmin, server credentials | Needed two connection configs: local (root / blank) for XAMPP and remote (school host) when deployed. | 100%
6 | 2025-10-17 | Backend Endpoints (PHP) | Create endpoints fetch_courses.php, fetch_attendance.php, and insert_attendance.php to provide/accept JSON and interact with DB. | PHP docs, prepared statements guide | insert_attendance.php uses prepared statements for safety; endpoints return JSON for the dashboard. | 100%
7 | 2025-10-18 | Deploy to School Server (FileZilla) | Upload project folder (activity_03/individual) via FileZilla into the school web root; ensure files are reachable via server URL. | FileZilla instructions, server host/username | Must place files under web root (e.g., ~youruser/activity_03/individual/); server may require different DB credentials. | 100%
8 | 2025-10-18 | Populate courses Table (Data) | Insert initial course rows so dropdowns are usable (sample data for demo). | courses.json (backup), phpMyAdmin | If dropdown shows "Select course" then table was empty — fixed by inserting sample rows. | 100%
9 | 2025-10-18 | GitHub Commit & Repository Form | Initialize Git repo, push project to GitHub, and complete required submission form with repo link + access info (usernames/tokens as requested). | GitHub docs, git CLI, assignment submission form | Remember: do NOT commit sensitive tokens directly to the repo. Use the form to share tokens if required and allowed. | 100%
10 | 2025-10-18 | Testing & Debugging | End-to-end testing: add attendance, fetch attendance list, verify UI and DB writes, and check on both local and remote servers. | Browser DevTools, phpMyAdmin, XAMPP | Debug steps: check fetch network calls, PHP errors, and DB authentication. | 90%

## file_guide
Date Agreed | Files | Description | Group Contribution
2025-10-15 | faculty_dashboard.php | Main Faculty Intern Dashboard page structure with header, sidebar, and content area. | HTML code provided by group (from Activity 2).
2025-10-15 | faculty_dashboard.css | Main stylesheet controlling dashboard colors, fonts, grid layout, and responsiveness. | CSS code sourced from Activity 2.
2025-10-16 | The_Dashboard.js | Handles dynamic content loading, user interactions, and fetch requests to PHP backend. | Code adapted from Activity 2.
2025-10-16 | database.php | Establishes connection to MySQL database for fetching dashboard data. | Provided template code for DB connection.
2025-10-16 | fetch_courses.php | Fetches available courses from database and returns data for dashboard display. | Discussed query structure.
2025-10-17 | attendance.php | Handles taking attendance for selected courses. | Suggested overall structure.